## SCE-Team
S. No. | Open Issues | Area | IT Track | Action planned / Task to be completed | Responsibility Team | Owner for Closure | Target Date
1 | Despatch from Naroda to COCO and Sales Return | Outbound / Inbound | Retail IT / SCE IT | - Shipments details to be identified for COCO Movements - System mapping and Trips to be created for transport settlement in 417 server | Sh. Vishesh Malviya Sh. Manoj Dash Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Keith Boodle Sh. Nirav Modi | Sh. Keith Boodle
2 | Despatch from COCO to COCO | Outbound | Retail IT / SCE IT | - Shipments details to be identified for COCO Movements - System mapping and Trips to be created for transport settlement - STO movement to be identified and its settlement process in 417 server | Sh. Vishesh Malviya Sh. Manoj Dash Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Keith Boodle Sh. Nirav Modi | Sh. Keith Boodle
3 | Despatch from Naroda to FOFO / Domestic despatches | Outbound | SCE IT | - Outbound process to be followed, since despatches from RP2 server - System already in place for outbound settlement - Teething issues for vendor settlement to be solved by IT team on SOS basis | Sh. Rajesh Chaubey Sh. Jitendra Sreekakulam Sh. Rakesh Chaudhary Sh. Ajay Sangal | Sh. Vishesh Malviya | 2019-08-02
4 | Saree Despatch (417 server - COCO) | Outbound | Retail IT / SCE IT | - Shipments details to be identified for Saree despatches - System mapping and Trips to be created for transport settlement | Sh. Vishesh Malviya Sh. Manoj Dash Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Keith Boodle Sh. Nirav Modi Sh. Jitendra Sreekakulam | Sh. Keith Boodle
5 | Saree Despatch (RP2 Server) | Outbound | SCE IT | - Shipments details to be identified for Saree despatches - System mapping required such as shipping point and transport planning point for saree despatches for transport settlement from Job work location to customers | Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Rajesh Chaubey Sh. Jitendra Sreekakulam | Sh. Vishesh Malviya
6 | Wool Movement - Job worker to Naroda plant | Inbound | SCE IT | - Wool movement from Job work location i.e. Ludhiana and Hoogly - 2 shipments created for above locations in production server for settlement of the vendor, currently under testing | Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Rajesh Chaubey Sh. Jitendra Sreekakulam Sh. Sridhar Titti | Sh. Vishesh Malviya | 25/1/19
7 | Raw Material - Yarn & Fibre (Domestic movement) | Inbound | SCE IT | - Inbound transporters have not started claiming their bills through e-biz portal - SCE IT team to confirm whether system is already in place or development required | Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Rajesh Chaubey Sh. Jitendra Sreekakulam Sh. Sridhar Titti | Sh. Manoj Dash
8 | Raw Material - Yarn (Domestic movement) from RIL sites i.e. Silvassa | Inbound | SCE IT | - Inbound transporters have not started claiming their bills through e-biz portal - SCE IT team to confirm whether system is already in place or development required | Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Rajesh Chaubey Sh. Jitendra Sreekakulam Sh. Sridhar Titti | Sh. Manoj Dash
9 | Raw Material - Yarn & Fibre from Vendor to Job work (Movement from Alok Industries to MAA Ashish) | Inbound | SCE IT | - Necessary documents already shared with IT team - System mapping required for vendor settlement form Vendor to Job work location and then from Job work location to RIL Naroda - SCE IT team to confirm system readiness | Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Rajesh Chaubey Sh. Jitendra Sreekakulam Sh. Sridhar Titti | Sh. Manoj Dash
10 | Raw Material - Yarn & Fibre from Job worker to RIL Naroda | Inbound | SCE IT | - System is already in place - couple of shipments created from Job work location to RIL Naroda for vendor settlement which is currently under testing - SCE IT team to confirm whether system is already in place or development required | Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Rajesh Chaubey Sh. Jitendra Sreekakulam Sh. Sridhar Titti | Sh. Manoj Dash
11 | Inbound movement of Engineering spares / Packing material / Chemicals (Locally) | Inbound | SCE IT | - System is already in place - couple of shipments created from Job work location to RIL Naroda for vendor settlement which is currently under testing - SCE IT team to confirm whether system is already in place or development required | Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Rajesh Chaubey Sh. Jitendra Sreekakulam Sh. Sridhar Titti | Sh. Manoj Dash
12 | Inbound movement of Chemicals (Domestic) | Inbound | SCE IT | - System is already in place - couple of shipments created from Job work location to RIL Naroda for vendor settlement which is currently under testing - SCE IT team to confirm whether system is already in place or development required | Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Rajesh Chaubey Sh. Jitendra Sreekakulam Sh. Sridhar Titti | Sh. Manoj Dash
13 | Inbound for Fabric goods (Domestic) | Inbound | SCE IT | - System is already in place - couple of shipments created from Job work location to RIL Naroda for vendor settlement which is currently under testing - SCE IT team to confirm whether system is already in place or development required | Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Rajesh Chaubey Sh. Jitendra Sreekakulam Sh. Sridhar Titti | Sh. Manoj Dash
14 | Outbound movement of Fabric/Yarn /Eng Spares/ Dyes & Chemicals (Domestic) - Purchase return | Outbound | SCE IT | - Awaiting inputs from IT team for OGP realted transactions for Purchase return | Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Rajesh Chaubey Sh. Jitendra Sreekakulam | Sh. Manoj Dash
15 | Inbound for Garments (Domestic) | Inbound | SCE IT | - System is already in place - Couple of shipments created from Job work location to RIL Naroda for vendor settlement which is currently under testing - SCE IT team to confirm whether system is already in place or development required | Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Rajesh Chaubey Sh. Jitendra Sreekakulam | Sh. Manoj Dash
16 | Outbound (Re-export) of Spare parts / machineries / Chemicals | Outbound | SCE IT | -Re-export of spare parts / chemicals especially to Europe (Spares), China, Japan etc and Taiwan (Chemicals) - Annual movement is about 2 MT - Mostly Air shipments for Spare shipments - Mostly sea shipments for Chemicals - Above movements is happening through OGP - SCE IT team to confirm whether system is already in place or development required | Sh. Rakesh Chaudhary Sh. Ajay Sangal Sh. Rajesh Chaubey Sh. Jitendra Sreekakulam | Sh. Manoj Dash
17 | Transport Settlement | Outbound | SCE IT | - System is ready for outbound settlement - Freight Mismatch error / Contract related issues to be taken care by P&C Team - Minor IT issues such as Slow performance of portal, Multiple selection of shipments etc | Sh. Rajesh Chaubey Sh. Manoj Dash Sh. Sridhar Titti Sh. Rakesh Chaudhary | Sh. Vishesh Malviya | 2019-08-02

## SD-Team
S. No. | Open Issues | Area | IT Track | Action planned / Task to be completed | Responsibility Team | Owner for Closure | Target Date | Remarks_SD_230119
1 | Shipping Instructions for Advance payments |  | SD | Absence of maker checker in SI scrolling as same person is doing scrolling and activation | Sh. Amit Dalmiya |  | 2018-12-24 | Process Related
2 | Manual Entry of Shipping bill data in SAP |  | SD | Total value of shipping bill is auto populated field in SAP and which should exactly match with the original shipping bill. However, in the existing system, total value does not match with actual SB value resulting into wrong scrolling of SB's in system. Due to this system error, users are not able to punch the correct values in the system. Export | Sh. Amit Dalmiya |  | 1. 01.01.2019 2. 24.12.2018 | WIP;30th
3 | DBK Value updation in Shipping bill |  | SD | DBK value are not entered in the shipping bill scrolling screen due to non availability of DBK rates in the sales order. | Sh. Amit Dalmiya |  | 24.12.2018 | UAT
4 | DBK Accrual accounting |  | SD | Existing auto DBK accounting programme is not used due to unavailability of DBK value in shipping bill scroll | Sh. Amit Dalmiya |  | 01.01.2019 | FCA
5 | Mutiple Tax invoice in Single commercial Invoice (Exports) |  | SD | Multiple commercial invoices are generated against the single B/L with manual insertions. | Sh. Amit Dalmiya |  | 24.12.2018 | UAT
6 | E-BRC Verification (Exports) |  | SD | e BRC module is not showing the accurate value of shipping bill in the system. Due to incorrect value, users are not able to upload and verify the e BRC. Delay in E BRC is also delaying the MEIS claim process | Sh. Amit Dalmiya |  | 24.12.2018 | FCA
7 | Banking document details updation in SAP (Exports) |  | SD | Existing functionality is not being used by the FC&A team | Sh. Amit Dalmiya |  |  | FCA
8 | Insurance certificate for Export Movements |  | SD | Insurance certificate not getting generated for Export Plant Invoice | Sh. Amit Dalmiya |  | 24.12.2018 | FCA
9 | Export Logistics Settlement |  | SD | Export related expenses e.g. Ocean freight, THC charges, doc charges, CHA charges are not settled through Logistics settlement module since April-18. Adhoc payments are being made to vendors | Sh. Amit Dalmiya |  | 24.12.2018 | Logistics
10 | Physical Inventory Verification |  | SD | Physical stock verification was not carried out as a part of migration activities. | Sh. Amit Dalmiya |  | 31.12.2018 | NA
11 | Delivery challan for sample sale |  | SD |  | Lod2 / Sh Amit Dalmiya |  | 31.12.2018 | Already in place;Need more clarity